## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-03-08
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-08 | 10:00 | 11:00 | 1 | Review the prepared questions for the first client meeting | 1.Be more familiar with the project. 2.Prepare questions could improve the efficiency of the client meeting. | 1. The outcome is modifying the questions of all team members. 2. Next action is to meet with clients.
Tuesday | 2021-03-09 | 15:00 | 19:00 | 4 | 1. Meet with client. 2. Team review meeting | 1. Got the preferences and requirements of client for this project. 2. Discuss and review the meeting content. 3. Allocate tasks. | 1. Next action is to write meeting minutes and send it to our client. 2. Be more familiar with the discussed webpage examples. 3. Identified different tasks, and team members choose their tasks according to their preferences.
Wednesday | 2021-03-10 | 12:00 | 18:00 | 6 | 1.Write meeting minutes | Sending the minutes back to the client could let clients have a quick check, in case we confuse or misinterpreted their advice. | 1. Next action is to be more familiar with the discussed webpage examples(DBLP & Tobias Friedrich). 2. Prepare to design and construct our webpage.
Thursday | 2021-03-11 | 12:00 | 15:00 | 3 | 1.Learn how to use Axure, which is a Powerful prototyping software. | According to the clients' requirements design a webpage demo, which could be used in the next client meeting. | 1. Next action is to learn how to use the Axure software, and prepare to design the webpage.
Friday | 2021-03-12 | 20:00 | 23:00 | 3 | Design the webpage demo | Design a demo could visiualise the requirements of clients and specify the needs of clients. | 1. Next action is to complete the demo design.
Saturday | 2021-03-13 | 13:00 | 18:00 | 5 | 1.Design the mind map for this project. 2. Design the webpage demo. | Mind map could make the framework of our project more clear and easy to desmonstrate with clients. | 1. The first outcome is the mind map, and we will discuss it with clients in the second client meeting. 2. The second outcome is the demo, which could specify and visulise the clients' requirements.
Sunday | 2021-03-14 | 12:30 | 14:30 | 2 | Team meeting:1. Discuss the framework of this project; 2. Discuss the demo | 1. Review our work in this week and prepare questions for the second client meeting, which could improve the meeting efficiency. | 1. Next action is to meet with client and discuss the framework and demo with clients
|  |  | Total | 24