## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-03-15
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 10:00 | 11:00 | 1 | Review the prepared questions for the first client meeting | 1.Prepare for the first week presentationt. 2.Prepare questions could improve the efficiency of the client meeting. | 1. The outcome is modifying the questions of all team members. 2. Next action is to meet with clients.
Tuesday | 2021-03-16 | 15:00 | 19:00 | 4 | 1. Second client meeting: present the framework of our project and the demo designed by Axure. 2. Group meeting | 1. Requirements specification 2. Discuss and review the meeting content. 3. Allocate tasks. | 1. In terms of back-end, clients donot prefer SQL. 2. In the next client meeting, we need to present a user interface demo of our project. 3. Identified different tasks, and team members choose their tasks according to their preferences.
Wednesday | 2021-03-17 | 12:00 | 18:00 | 6 | 1. Redesign the user interface of our project according to clients feedback. 2. Learn how to use HTML, CSS programming languages. | Redesign the user interface could help team members know how to structure our code. | 1. Next action is to design our user interface and code.
Thursday | 2021-03-18 | 12:00 | 15:00 | 3 | 1.Design the main page interface of our project. | Following the example provided by clients, design the main page user interface. | 1. Next action is to design publications page.
Friday | 2021-03-19 | 20:00 | 23:00 | 3 | Design the publications webpage. | Design a demo could visiualise the requirements of clients and specify the needs of clients. | 1. Next action is to link the webpage to the html file generated from the back-end.
Saturday | 2021-03-20 | 13:00 | 16:00 | 3 | 1.Communicate with another team member and organise all webpages together using a navigation bar. | Complete the webpage design tasks, which will be presented in the third client meeting. | 1. The first outcome is the webpage demo and we will present it in the second client meeting. 2. In the next stage, if we receive feedback from clients, we will refactor our user interface.
Sunday | 2021-03-21 | 12:30 | 20:30 | 8 | Team meeting:1. Discuss the front-end design of this project; 2. Discuss the pitch presentation, including document and slides. 3. Make pitch presentation slides. | 1. Review our work in this week, which could improve the meeting efficiency. | 1. Next action is to meet with client and discuss the user interface demo with clients and receive their feedback. 2. Make ptch presentation slides in my part. 3. Send the pitch slides to clients and receive their feedback.
|  |  | Total | 28