## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1790432 |  | Week starting: | 2021-03-15
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2021-03-15 | 14:00 | 15:00 | 1 | Prepare for the first client meeting | Gather requirements | Next action is the first client meeting
Tuesday | 2021-03-16 | 15:00 | 19:00 | 4 | 1. first client meeting: present the framework of our project and the demo designed by Axure. 2. Group meeting | present the framework of our project and the demo | 1. In terms of back-end, clients donot prefer SQL. 2. In the next client meeting, we need to present a user interface demo of our project.
Wednesday | 2021-03-17 | 8:00 | 13:00 | 5 | Design the user interface, learning to use front-end framework | A scratch of the user interface | Discuss the scratch with team members
Thursday | 2021-03-18 | 13:00 | 18:00 | 5 | Design the user interface, learning to use front-end framework | A scratch of the user interface | Discuss the scratch with team members
Friday | 2021-03-19 | 20:00 | 22:00 | 2 | Discuss the scratch with team members . | Feedback has been gathered from tech leader. | Implementing user interface.
Saturday | 2021-03-20 | 13:00 | 16:00 | 3 | 1.Communicate with another team member and organise all webpages together using a navigation bar. | Complete the webpage design tasks, which will be presented in the third client meeting. | 1. The first outcome is the webpage demo and we will present it in the second client meeting. 2. In the next stage, if we receive feedback from clients, we will refactor our user interface.
Sunday | 2021-03-21 | 12:30 | 20:30 | 8 | Team meeting:1. Discuss the front-end design of this project; 2. Discuss the pitch presentation, including document and slides. 3. Make pitch presentation slides. | 1. Review our work in this week, which could improve the meeting efficiency. | 1. Next action is to meet with client and discuss the user interface demo with clients and receive their feedback. 2. Make ptch presentation slides in my part. 3. Send the pitch slides to clients and receive their feedback.
|  |  | Total | 28