## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1804981 |  | Week starting: | 2021-03-15
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-15 | 9:00 | 13:00 | 4 | Review questions for the first client meeting | 1.Look through all the pitch presenatation documents. 2.Prepare questions could improve the efficiency of the client meeting. | 1. The outcome is to be ready for the next day client meeting. 2. Next action is to meet with clients.
Tuesday | 2021-03-16 | 15:00 | 19:00 | 4 | 1. Second client meeting: show client our team framework and how we can fullfill their needs. 2. Group meeting | 1. Understand client needs 2. Discuss and review the meeting content. 3. Allocate tasks with my group members | 1.Our client prefer our font-end to make something real before the next group meeting 2. In the next client meeting, we need to present a web page to show them how our web looks like.
Wednesday | 2021-03-17 | 11:00 | 14:00 | 5 | Learn HTML & CSS | Throught learning HTML, I can have an idea about the structure of the web page. | Next action is to design our web through HTML
Thursday | 2021-03-18 | 12:00 | 15:00 | 3 | 1.Design the main page interface of our project. | Following the example provided by clients, design the main page user interface. | 1. Next action is to design publications page.
Friday | 2021-03-19 | 6:00 | 9:00 | 3 | Design the publications and research webpage. | Design a web publication page fullfill the needed of our client. | Next action is to link the webpage
Saturday | 2021-03-20 | 13:00 | 16:00 | 3 | Communicate with Ying Li and Bruce Hou to design a nav bar for our font-end web page | A framwork our our font-end webpage came out | The next step is to try to make hyperlinks more detailed in the same path.
Sunday | 2021-03-21 | 10:00 | 18:00 | 8 | Team meeting: Discuss the front-end design and pitch presentation PPT | 1. Review our work in this week, make sure that we stand in the same point | 1. Next action is to meet with client and combine each team members PPT as a whole project.
|  |  | Total | 30