## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-03-29
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-03-29 | 10:00 | 11:00 | 1 | Review the prepared questions for the third client meeting. | 1.Prepare for the third week presentationt. 2.Prepare questions for the third client meeting. | 1. The outcome is modifying the questions of all team members. 2. Next action is to meet with clients.
|  | 15:00 | 16:00 | 1 | Review the agenda. | Summarise the project progress that we have made in the last week, which could help us record the project progress. | Complete the agenda and send it to clients.
Tuesday | 2021-03-30 | 16:00 | 19:30 | 3.5 | 1. Check the checklist and requirements of Business Case & Draft Plan. | Be more clear with the requirements of Business Case & Draft Plan. | Next action is to write the Business Case & Draft Plan.
Wednesday | 2021-03-31 | 15:00 | 16:00 | 1 | 1. Do more research about the Tobias website, group members' website in the university of adelaide. | Found every staff has their own homepage and publciations page. | Next action is to design the demo of homepage for researchers.
Thursday | 2021-04-01 | 14:00 | 15:00 | 1 | 1.Communicate with Bruce and decide how to concatenate the back-end and front-end. | Fulfill the requirements of clients | 1. The outcome is finishing the connection of the front end and back end.
Friday | 2021-04-02 | 14:00 | 20:00 | 6 | 1. Write the executive summary and importance part of Business Case & Draft Plan. | The executive summary is the most important part in the documentation. The importance part is the first main part in the documentation. | 1. The outcome is generally complete the Business Case & Draft Plan.
Saturday | 2021-04-03 | 13:00 | 16:00 | 3 | 1. Review the Business Case & Draft Plan. | Review the documentation could make our report easy to understand. | 1. The outcome is the Business Case & Draft Plan.
Sunday | 2021-04-04 | 23:30 | 14:00 | 2.5 | Team meeting:1. Review the Business Case and Draft Plan; 2. Review the project progress that we made in the last week; 3. Discuss the functionalities that we need to implement in the next week. | 1. Finished the documentation part, which made our milestone one more clear; 2. Review our work in this week, which could improve the meeting efficiency. | 1. The outcome is submitting the Business Case & Draft Plan documentation.
|  | 16:00 | 0:30 | 8.5 | 1. Design the researchers page and the homepage for eack researchers; 2. Help Bruce sort publications by the types of publications. | 1. Designed the structure of researchers page ; 2. Publications could be correctly displayed by year. | Next action is to meet with clients and decide do we need to design the homepage of researchers/
|  |  | Total | 27.5