## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-04-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-05 | 10:00 | 11:00 | 1 | Review the prepared questions for the third client meeting. | 1.Prepare for the third week presentationt. 2.Prepare questions for the third client meeting. | 1. The outcome is modifying the questions of all team members. 2. Next action is to meet with clients.
|  | 14:00 | 17:00 | 3 | Design the homepage of researchers. | Design the prototype of researchers webpage. | Complete the prototype design of researchers homepage.
Tuesday | 2021-04-06 | 15:30 | 16:00 | 0.5 | 1. Meet with clients: present the project progress and receive their feedback. | The regular client meeting. | Next action is to hold the team meeting and discuss how to implement the requirements of clients.
|  | 17:00 | 19:30 | 2.5 | 1. Team meeting: discuss how to implement the search function according to clients' requirements. | Satisfy all demands of clients. | Next action is to implement the filter function in publications webpage.
Wednesday | 2021-04-07 | 13:00 | 16:00 | 3 | 1. Write meeting minutes for the client meeting and send to clients. | Record all meeting content and manage the project progress effectively. | Next action is to work with team members and implement the filter function.
Thursday | 2021-04-08 | 14:00 | 15:00 | 1 | 1.Communicate with Bruce and decide how to implement the filter function. | Fulfill the requirements of clients | 1. Next action is to learn more knowledge about js and css.
Friday | 2021-04-09 | 14:00 | 20:00 | 6 | 1. Learn to implement filter in the publications webpage. | Fulfill the requirements of clients | 1. The outcome is know how to design the filter.
Saturday | 2021-04-10 | 13:00 | 14:00 | 1 | 1. Beautify the user interface of our website. | Make the website more logical. | 1. Next action is to meet with team members.
Sunday | 2021-04-11 | 10:00 | 12:00 | 2 | Team meeting:1. Discuss the front-end fliter design. 2. Discuss the data acquire problems. | 1. Implemented the requirements of clients. | 1. The outcome is adding filter function in publications webpage according to clients' requirements.
|  | 16:00 | 22:00 | 6 | 1. Beautify the user interface of publications webpage. | 1. Make the publicaitons webpage more beautiful. | Next action is to edit the front end webpage according to back-end implementation.
|  |  | Total | 26