## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-04-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-26 | 12:00 | 14:00 | 2 | Write the agenda for the fifth client meeting. | 1. Sumarise the work that we have done in the last two week and the issues that we want to discuss with client in the client meeting. | 1. The outcome is sending agenda to clients.
|  | 18:00 | 0:00 | 6 | Refactor the front-end code for checkbox. | Satisfy all demands of clients(filter function). | The filter function can work correctly.
Tuesday | 2021-04-27 | 23:00 | 15:00 | 4 | 1. Work with Yupeng Hou and He Zhang to debug the front-end code and parser. | Increase the accuracy of the displayed publications. | Next action is to meet with client.
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and discuss some issues with clients. | Finished the planned activities of milestone 1 and implement more functionalities according to clients' requirements. | Next action is hold a team meeting.
|  | 17:00 | 18:00 | 1 | 1. Team meeting: discuss how to implement the login function according to clients' requirements. | Satisfy all demands of clients. | Next action: 1. Send a test version of the project to clients. 2. Implement the login function. 3. Check the same publications and only display once in the Publications webpage.
Wednesday | 2021-04-28 | 13:00 | 16:00 | 3 | 1. Write meeting minutes for the fifth client meeting and send to clients. | Record all meeting content and list all tasks that we will do in the next week. | Next action is to contact clients and ask how to send our project to them(GitHub link or docker?)
Thursday | 2021-04-29 | 21:00 | 2:00 | 5 | 1.Discuss with Yupeng Hou about the Milestone1 report and write the document. | Complete the required document of the project. | 1. The outcome is finishing the draft of the Milestone 1 report.
Friday | 2021-04-30 | 18:00 | 19:30 | 1.5 | 1. Join the Q&A session and ask Cruz for feedback about the Milestone1 report. | Make the report more clear and concise. | 1. The outcome is get the feedback of the report.
Saturday | 2021-05-01 | 22:30 | 15:30 | 5 | 1. Team meeting: Discuss the implementation of the login function including back-end and front-end. | Meet the requirements of clients. | 1. The outcome is have a clear structure of the implementation of the login function.
Sunday | 2021-05-02 | 10:00 | 12:00 | 2 | Rewrite the milestone 1 report according to Cruz's feedback. | 1. Make the report more clear and concise. | 1. The outcome is completing the milestone 1 report.
|  | 16:00 | 22:00 | 6 | 1. Beautify the user interface of publications webpage. | 1. Make the publicaitons webpage more beautiful. | Next action is to edit the front end webpage according to back-end implementation.
|  |  | Total | 36