## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1804981 |  | Week starting: | 2021-04-26
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-04-26 | 8:00 | 14:00 | 6 | design the webpage login part | A login page will allow user to store their information in our webpage | The outcome is to design a login page. Next action is to write python/PHP code and run it
Tuesday | 2021-04-27 | 15:00 | 19:00 | 4 | 1. Meet with client. 2. Team review meeting | After meet with client, we know the target of the project and then we have a group meeting after client meeting | The next action is to record the meeting and debug for the login page
Wednesday | 2021-04-28 | 10:00 | 14:00 | 4 | debug for the login page | to make sure the PHP code could run. | The Next action is to email Markus the Frank Page
Thursday | 2021-04-29 | 13:00 | 16:00 | 3 | filter debug | There are so many problem in our filter part | The Next action is to working on the filter
Friday | 2021-04-30 | 11:00 | 17:00 | 6 | filter debug and funtion change | make our filter logical | The Next action is to be ready for the group meeting
Saturday | 2021-05-01
Sunday | 2021-05-02 | 9:00 | 16:00 | 7 | Team meeting:1. Discuss the login page and filter for the font-end webpage | Meeting with team members to summarize the work tasks of this week will help to promote the progress of the project JS is the main part and most difficult things for us now | The Next action is to finish the function of the filter and sprepared for the next week client meeting
|  |  | Total | 30