## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-05-03
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-03 | 11:00 | 12:00 | 1 | Communicate with Arnold and discuss the | 1. Sumarise the work that we have done in the last two week and the issues that we want to discuss with client in the client meeting. | 1. The outcome is sending agenda to clients.
|  | 12:00 | 13:00 | 2 | Write the agenda for the sixth client meeting. | 1. Sumarise the work that we have done in the last week and the issues that we want to discuss with client in the client meeting. | 1. The outcome is sending agenda to clients.
|  | 17:00 | 6:00 | 1 | Test the prototype for the sixth meeting. | Make the prototype work correctly. | The outcome is fixing some bugs of the filter.
Tuesday | 2021-05-04 | 11:00 | 15:00 | 4 | 1. Work with WeiQin and Yupeng Hou to solve the peoblem of filter and managing researchers. | Increase the accuracy of the two functions. | Next action is to meet with client.
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and discuss some issues with clients. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 18:00 | 1 | 1. Team meeting: discuss how to implement the edit BibTex entries according to clients' requirements. | Satisfy all demands of clients. | Next action: 1. Implement the edit BibTex entries function. 2. Debug the filter function. 3. Write the final milestone plan and submit. 4. Redesign the user interface and combine the normal version and the admin version.
Wednesday | 2021-05-05 | 13:00 | 16:00 | 3 | 1. Write meeting minutes for the sixth client meeting and send to clients. | Record all meeting content and list all tasks that we will do in the next week. | Next action is to write the final milestone plan.
Thursday | 2021-05-06 | 21:00 | 0:00 | 3 | 1.Wrote the final milestone plan. | Complete the required document of the project. | 1. The outcome is finishing the final milestone plan and submit.
Friday | 2021-05-07 | 15:00 | 17:00 | 2 | Fix some bugs of the user interface, such as the footer, navigation bar and window size. | Make the user interface more clean. | 1. The outcome is finishing the user interface design.
Saturday | 2021-05-08 | 18:00 | 12:30 | 6.5 | Integrated the two version of the user interface. | Make the project suitable for all devices. | 1. The outcome is making the collapsing the navigation bar.
Sunday | 2021-05-09 | 11:30 | 20:00 | 9.5 | Debug the frontend and backend. | Make the project work correctly. | 1. The outcome is fixing the alert function, the blank space of "20" and the edit button.
|  |  | Total | 33.5