## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1790432 |  | Week starting: | 2021-05-03
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-03 | 15:00 | 5:00 | 2 | prepare the demo to present to the costomer | Make the prototype work correctly. | The demo functions as expected
Tuesday | 2021-05-04 | 11:00 | 15:00 | 4 | 1. Work with LiYing and Yupeng Hou to solve the peoblem of filter and managing researchers. | Increase the accuracy of the two functions. | Next action is to meet with client.
|  | 15:30 | 16:30 | 1 | Client meeting: present the previous work and discuss some issues with clients. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 18:00 | 1 | 1. Team meeting: discuss how to implement the edit BibTex entries according to clients' requirements. | Satisfy all demands of clients. | Next action: 1. Implement the edit BibTex entries function. 2. Debug the filter function. 3. Write the final milestone plan and submit. 4. Redesign the user interface and combine the normal version and the admin version.
Wednesday | 2021-05-05 | 15:00 | 18:00 | 3 | Write the filter function that can help user to get the result |  | Next action is to test the filter
Thursday | 2021-05-06 | 15:00 | 6:00 | 3 | Test the filter in all researcher's homepage, fix some bugs that cause the elements to disappear |  | The user can now use the filter to get the result he wanted.
Friday | 2021-05-07 | 15:00 | 19:00 | 4 | Fix some bugs of the user interface, such as the footer, navigation bar and window size. | Make the user interface more clean. | The outcome is finishing the user interface design.
Saturday | 2021-05-08 | 15:00 | 19:00 | 4 | Integrated the two version of the user interface. | Make the project suitable for all devices. | The outcome is making the collapsing the navigation bar.
Sunday | 2021-05-09 | 2:30 | 20:30 | 6 | Debug the frontend and backend. | Make the project work correctly. | The outcome is fixing the alert function, the blank space of "20" and the edit button.
|  |  | Total | 28