## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-05-10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-10 | 11:00 | 12:00 | 1 | Communicate with Arnold and discuss the testing plan. | 1. Prepare for the work in the test phase. | 1. The outcome is that Arnold will finish the project overview and scope of testing plan firstly.
|  | 12:00 | 13:00 | 2 | Write the agenda for the seventh client meeting. | 1. Sumarise the work that we have done in the last week and the issues that we want to discuss with client in the client meeting. | 1. The outcome is sending agenda to clients.
|  | 17:00 | 6:00 | 1 | Test the prototype for the seventh client meeting. | Make the prototype work correctly. | The outcome is fixing some bugs of the managing researchers.
Tuesday | 2021-05-11 | 11:00 | 15:00 | 4 | 1. Work with WeiQin and Yupeng Hou to solve the peoblem of filter and managing researchers. | Increase the accuracy of the two functions. | Next action is to meet with client.
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and discuss some issues with clients. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 18:00 | 1 | 1. Team meeting: discuss how to deploy theproject to the server of our university. | Prepare for delivering the project. | Next action: 1. Communicate with clients and identify the access limitation of the server in our university.
Wednesday | 2021-05-12 | 13:00 | 16:00 | 3 | 1. Write meeting minutes for the seventh client meeting and send to clients. | Record all meeting content and list all tasks that we will do in the next week. | Next action is to meet with tutor for receiving the feedback of milestone 1.
|  | 17:00 | 18:00 | 1 | 1. Meeting with tutor and receive feedback for milestone 1; 2.Team meeting: discuss the tasks that we need to do in this week. | Focus on the testing plan. | Next action is to design test case and finish the draft of test plan.
Thursday | 2021-05-13 | 21:00 | 0:00 | 3 | 1.Check with client and discuss the deployment issue. | Have a solution to deploy the project. | 1. The outcome is having a solution to deploy the project.
Friday | 2021-05-14 | 20:00 | 22:00 | 2 | Fix some bugs of the project. | Make the project work correctly. | 1. The outcome is solving the internal server error.
Saturday | 2021-05-15 | 12:00 | 18:30 | 6.5 | Design the log webpage and debug with Bruce. | The end phase of the project. | 1. The outcome is add the log webpage, which display parser_log and bib_change_log.
Sunday | 2021-05-16 | 11:30 | 20:00 | 9.5 | Team meeting; Write route for log webpage; Debug the frontend and backend. | Make the project work perfect. | 1. The outcome is that the project could be deployed in the server .
|  |  | Total | 34.5