## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1790432 |  | Week starting: | 2021-05-03
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-03 | 11:00 | 12:00 | 1 | Communicate with Bruce and discuss the testing plan. |  | Get an overview of how to write the test plan.
Tuesday | 2021-05-04 | 11:00 | 15:00 | 4 | 1. Work with WeiQin and Yupeng Hou to solve the peoblem of filter and managing researchers. | Increase the accuracy of the two functions. | Next action is to meet with client.
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and discuss some issues with clients. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 18:00 | 1 | 1. Team meeting: discuss how to deploy theproject to the server of our university. | Prepare for delivering the project. | Next action: 1. Communicate with clients and identify the access limitation of the server in our university.
Wednesday | 2021-05-05 | 8:00 | 13:00 | 5 | Write the Unit test plan |  | The unit test plan is finished, the next step is to write integraton test plan
|  | 8:00 | 0:00 | 2 | Write the integration test plan |  | Finished the integration test plan, next action is to design test case and finish.
Thursday | 2021-05-06 | 21:00 | 0:00 | 3 | 1.Check with client and discuss the deployment issue. | Have a solution to deploy the project. | The outcome is having a solution to deploy the project.
Friday | 2021-05-07 | 12:00 | 14:00 | 2 | Start reading heroku deploying guide |  | A draft plan for deploying the project has been finished.
Saturday | 2021-05-08 | 20:00 | 14:00 | 6 | Modify the project to get ready to deploy to the server. |  | The project can now be started from the server side, but some functions is not function correctly.
Sunday | 2021-05-09 | 0:00 | 19:00 | 7 | Modify the project to let it run on the server side. |  | Most of the functions can function as expected, more test is needed to test on the server side.
|  |  | Total | 31.5