## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1804981 |  | Week starting: | 2021-05-10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-10 | 11:00 | 12:00 | 1 | Communicate with YingLi and discuss the testing plan. | 1. Prepare for the work in the test phase. | 1. The outcome is that Arnold will finish the project overview and scope of testing plan firstly.
|  | 17:00 | 20:00 | 3 | finish the project overview and scope | test plan needed | The outcome is finishing the overview and scope part of the test plan
Tuesday | 2021-05-11 | 11:00 | 15:00 | 4 | 1. Work with Team to solve the peoblem of filter and managing researchers. | Increase the accuracy of the two functions. | Next action is to meet with client.
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and discuss some issues with clients. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 19:00 | 2 | 1. Team meeting: | Prepare for delivering the project. | Next action: keep writing the testing plan
Wednesday | 2021-05-12 | 13:00 | 16:00 | 3 | 1. Write meeting the next part of the testing plan. | Record all client need for the next weenk | Next action is discuss with YingLi about the testing plan
|  | 17:00 | 18:00 | 1 | 1. Meeting with tutor 2.Team meeting: | Focus on the testing plan. | Next action is to finish the testing plan
Thursday | 2021-05-13 | 21:00 | 0:00 | 3 | 1.meeting with YingLi to see a solutuon for deploying the project | find a solution. | 1. The outcome is having a solution to deploy the project.
Friday | 2021-05-14 | 13:00 | 15:00 | 2 | change the testing plan | Make the testing plan better | 1. The outcome is making the testing plan easy to read
Saturday | 2021-05-15 | 9:00 | 14:00 | 5 | Design the loging page and give it to back-end | finish the login page of mine part | 1. The outcome is add the log webpage, which display parser_log and bib_change_log. But YingLi and Yupeng Hou changed type of mine login page
Sunday | 2021-05-16 | 11:30 | 14:30 | 3 | Team meeting; Write route for log webpage; Debug the frontend and backend. | Make the project work perfect. | 1. The outcome is that the project could be deployed in the server .
|  |  | Total | 27.5