## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1790432 |  | Week starting: | 2021-05-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-17 | 8:00 | 21:00 | 1 | Communicate with Bruce about the bugs in base_publicagtions. |  | Fixed the bugs in base_publications.html.
|  | 19:00 | 10:00 | 3 | Fixed bugs with Bruce and implemented the double check function when users want to delete a researcher. |  | The outcome is fixing some bugs of the managing researchers, and implemented a version of double check.
Tuesday | 2021-05-18 | 10:00 | 13:00 | 3 | 1. Work with Yupeng Hou to improve the function of double check. | Increase the accuracy of the this function. | Next action is to meet with client.
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and discuss some issues with clients. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 18:00 | 1 | 1. Team meeting: discuss how to implement the function of hiding entries, displaying each fields of an entry. | Implement more functions according to the feedback of clients. | Next action: Communicate with clients about the format of displaying each fields of an entry.
Wednesday | 2021-05-19 | 17:00 | 19:00 | 2 | 1. Work with Yupeng Hou to fix bugs in the filter function. | Improve the performance of the filter function.
Friday | 2021-05-21 | 0:00 | 19:00 | 7 | Implement the parser log |  | parser log implemented, all modifications on the system will be logged
Saturday | 2021-05-22 | 0:00 | 17:00 | 5 | Finish writing the test plan |  | Test plan is now finished and submitted
Sunday | 2021-05-23 | 11:30 | 17:00 | 5.5 | Team meeting; Write route for log webpage; Debug the frontend and backend. | Make the project work perfect. | 1. The outcome is fixing all bugs of the project.
|  |  | Total | 28