## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1804981 |  | Week starting: | 2021-05-17
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-17 | 11:00 | 12:00 | 1 | Communicate with team about the bugs in base_publicagtions. | 1. Make the project better. | 1. Fixed the bugs in base_publications.html.
|  | 19:00 | 10:00 | 3 | Fixed bugs with Team and implemented the double check function . | Make the prototype better | The outcome is fixing some bugs of the managing researchers, and implemented a version of double check.
Tuesday | 2021-05-18
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and discuss some issues with clients. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 18:00 | 1 | 1. Team meeting: discuss how to implement the function of hiding entries, displaying each fields of an entry. | Implement more functions according to the feedback of clients. | Next action: Communicate with Yingli about the testing plan final version
Wednesday | 2021-05-19 | 13:00 | 16:00 | 3 | 1. Write meeting minutes for the eighth client meeting and send to clients. | Record all meeting content and list all tasks that we will do in the next week. | Next action is to test and write the testing plan.
|  | 17:00 | 19:00 | 2 | 1. Work with Team to fix bugs in the filter function. | Improve the performance of the filter function. | Next action is to finish the testing plan
Thursday | 2021-05-20
Friday | 2021-05-21 | 10:00 | 17:00 | 7 | Writing the testing plan with Yingli | Finish an important document of this course. | 1. The outcome is finishing the testing plan.
Saturday | 2021-05-22 | 10:00 | 12:30 | 2.5 | Double check the content in testing plan with YingLi | Make the testing plan more clear and concise. | 1. The outcome is a final version of testing plan.
Sunday | 2021-05-23 | 11:30 | 17:00 | 5.5 | Team meeting; Write route for log webpage; Debug the frontend and backend. | Make the project work perfect. | 1. The outcome is fixing all bugs of the project.
|  |  | Total | 25.5