## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-05-24
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-24 | 18:00 | 21:00 | 3 | Modify the appendix of the testing plan. | Make the testing plan clear and concise. | 1. The outcome is submitting the testing plan
|  | 12:00 | 13:00 | 2 | Write the agenda for the ninth client meeting. | 1. Sumarise the work that we have done in the last week and the issues that we want to discuss with client in the client meeting. | 1. The outcome is sending agenda to clients.
Tuesday | 2021-05-25 | 11:00 | 15:30 | 3.5 | 1. Design the survey and prepare for the client meeting. | Receive feedback from clients and peers, which could help the project become better. | Next action is to meet with client.
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and discuss some issues with clients. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 21:00 | 4 | 1. Team meeting: discuss how to deploy the project to the server of our university. 2. Design a new survey according to the tutor's suggestions. | Prepare for delivering the project. | Next action: 1. Communicate with clients and identify the access limitation of the server in our university. 2. Send the survey to clients.
Wednesday | 2021-05-26 | 13:00 | 16:00 | 3 | 1. Write meeting minutes for the ninth client meeting and send to clients. | Record all meeting content and list all tasks that we will do in the next week. | Next action is to improve the user interface of AGUP management system.
Thursday | 2021-05-27 | 21:00 | 0:00 | 3 | 1.Check with client and discuss the deployment issue. | Have a solution to deploy the project. | 1. The outcome is having a solution to deploy the project.
Friday | 2021-05-28 | 20:00 | 22:00 | 2 | Fix some bugs of the project. | Make the project work correctly. | 1. The outcome is solving the wrong input year in 'add researcher' webpage.
Saturday | 2021-05-29 | 12:00 | 15:00 | 3 | Beautify the user interface and debug with Bruce. | The end phase of the project. | 1. The outcome is adding more instructions in the AGUP management system, and adjust the size of the update button.
Sunday | 2021-05-30 | 11:30 | 16:00 | 4.5 | Team meeting; Design poster. | Design poster for the project. | 1. The outcome is finishing the draft of the poster.
|  |  | Total | 28.5