## Sheet2
MCI Project Weekly Time Sheet
Team | Team 21 | Student ID |  | a1776903 |  | Week starting: | 2021-05-31
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2021-05-31 | 18:00 | 21:00 | 3 | Design poster | Design poster for the project | 1. The outcome is finishing the design of the poster and waiting for the clients' feedback.
|  | 12:00 | 13:00 | 2 | Write the agenda for the tenth client meeting. | 1. Sumarise the work that we have done in the last week and the issues that we want to discuss with client in the client meeting. | 1. The outcome is sending agenda to clients.
Tuesday | 2021-06-01 | 13:00 | 15:30 | 2.5 | 1. Prepare for the client meeting. | Receive feedback from clients, which could help the project become better. | Next action is to meet with client.
|  | 15:30 | 16:00 | 0.5 | Client meeting: present the previous work and receive feedbacks. | Meet all demands of clients and implement more functionalities according to clients' requirements. | Next action is holding a team meeting.
|  | 17:00 | 21:00 | 4 | 1. Team meeting: discuss how to deploy the project to the server of our university. 2. Delete some text in the poster. | Prepare for delivering the project. | Next action: Try nginx on our own computer and figure out how to deploy the project on the university's server.
Wednesday | 2021-06-02 | 13:00 | 16:00 | 3 | 1. Write meeting minutes for the tenth client meeting and send to clients. | Record all meeting content and this is the last client meeting. | Next action is to try to use nginx to deply the project.
Thursday | 2021-06-03 | 11:00 | 12:00 | 1 | 1.Send email to Markus about the solution of deploying the project to the university's server. | Have a solution to deploy the project. | 1. The outcome is having a solution to deploy the project.
Friday | 2021-06-04 | 16:00 | 22:00 | 6 | Redesign the poster according to Cruz's feedback. | Make the poster more concise and clear. | 1. The outcome is finishing the design of the poster.
Saturday | 2021-06-05 | 12:00 | 13:00 | 1 | Redesign the poster according to Cruz's feedback. | Make the poster more concise and clear. | 1. The poster is completed.
Sunday | 2021-06-06 | 6:00 | 20:00 | 2 | Modify the poster according to Arnold and Wei Qin's feedback. | Edit some small issues in the poster. | 1. The outcome is complete the final version of the poster.
|  |  | Total | 25